## Concerns + PPC Action Plan
Item # | Concern | Details | Start Date | End Date | RSO Comments | Mines Proposed Action Plan | PPC Comments | Test Results | Conclusion | Action Concluded
1 | Air Pollution | I am writing to express my deep concern regarding the air pollution, noise pollution associated with the operations of the PPC Laudium Quarry. As a resident of Christoburg, I have noticed a significant increase in dust and particulate matter in the air, which I believe is directly linked to the mining activities in our vicinity. |  |  | 31 Oct 2024_Health issues & Due to high electricity I was forced to install Solar as we are unable to leave windows open and have to run air conditioners. What assistance is the mine willing to consider until the issue is resolved? PPC - ??? 11 July 2025 - 2nd Meeting - No Comment as yet from PPC. PPC to respond
26 June 2025_A formal plan of mitigation regarding air and noise pollution and ground vibrations.
|  | The impact of this pollution on the health and well-being of our community is alarming. Many residents, including myself, have experienced respiratory issues, increased allergies, and other health complications that can be traced back to poor air quality. Additionally, the environmental consequences of such pollution are concerning; it affects local wildlife and vegetation, further degrading our natural surroundings. Not to mention the increase cost of maintenance of the property and vehicles. I’m unable to install Solar panels due to the regular maintenance it would require for optimum use. | 2024-10-25 |  | Recommandation: if PPC is unable to resolve by 31 December 2025. PPC to purchase property , bank evaluation. Reasons already tabled and discussed
I urge you to take immediate steps to mitigate the air pollution caused by your operations. Implementing stricter dust control measures, investing in cleaner technology, and ensuring compliance with environmental regulations are crucial steps that must be prioritized.
Transparency is essential in this matter. I request that you provide detailed information on the measures you are taking to address air quality concerns and the monitoring systems in place to ensure compliance with environmental standards.
REFER to all emails
2 | Noise Pollution | The persistent noise from the mine at very odd hours has significantly affected the quality of life for us at home. | 2024-10-25 |  | VIBRO could be the cause for this as indicated by the mine. RSO to follow up with brick factory 01 Nov 2024_Awaiting a response from VIBRO Investigation done NOT VIBRO 11 July 2025_ PPC GM advised that it's still VIBRO_RSO had advised contrary to that. RSO agreed to contact VIBRO. 14 July 2025 discussion with VIBRO. The Noise and vibrations are outside thier normal working hours. Hence the conclusion is that it's the mine.
26 June 2025_A formal plan of mitigation regarding air and noise pollution and ground vibrations.
|  | The continuous sounds of machinery, sirens, etc at odd hours of the night including weekends have not only disrupted our daily lives but have also led to increased stress, sleep deprivation and health issues. My family and I are finding it difficult to enjoy our home, especially during the evenings and weekends when we seek rest and relaxation. |  |  | Recommandation: if PPC is unable to resolve by 31 December 2025. PPC to purchase property , bank evaluation. Reasons already tabled and discussed
I urge you to take immediate action to mitigate the noise pollution caused by your operations. Implementing effective noise reduction strategies, such as sound barriers and limiting operational hours, could significantly improve the situation.
Furthermore, I would appreciate any information you can provide regarding your current noise monitoring practices and any plans you have to address this ongoing issue. Transparency and communication with us are vital to building a positive relationship moving forward.
REFER to all emails
3 | Vibrations | With regards to the vibrations caused by mining machinery and their impact on the structural integrity of my property. I have noticed significant disturbances resulting from your operations, which have begun to cause damage to my home. | 2024-10-25 |  | VIBRO could be the cause for this as indicated by the mine. RSO to follow up with brick factory 01 Nov 2024_Awaiting a response from VIBRO Investigation done NOT VIBRO 11 July 2025_ PPC GM advised that it's still VIBRO_RSO had advised contrary to that. RSO agreed to contact VIBRO. 14 July 2025 discussion with VIBRO. The Noise and vibrations are outside thier normal working hours. Hence the conclusion is that it's the mine.
26 June 2025_ A full and independent assessment of the structural damage caused to my property — at your expense.
|  | The vibrations from the heavy machinery and blasting activities are not only disruptive but have also led to visible cracks in the walls and ceilings of my property. This situation is distressing and has raised concerns about the long-term safety and stability of my home. |  |  | 26 June 2025_A formal plan of mitigation regarding air and noise pollution and ground vibrations.
|  | I urge you to take immediate action to assess and address the impact of these vibrations. Implementing mitigation strategies—such as adjusting operational procedures or enhancing vibration monitoring—could help prevent further damage. |  |  | Recommandation: if PPC is unable to resolve by 31 December 2025. PPC to purchase property , bank evaluation. Reasons already tabled and discussed
I would also appreciate any information you can provide regarding your current practices for monitoring vibrations and how you plan to address this issue moving forward. Open communication is crucial for fostering a positive relationship and ensuring that we feel safe in our home.
I have reason to believe that other residents in the community may be having the same issues.
REFER to all emails
Additional Notes provided by Home Owner
Actions taken by me:
| a | I had to replace all carpets with waterproof vinyl flooring as the carpets were getting damp due to cracks in the foundation believed to be caused by the vibrations caused by the mine. This was done post waterproofing works. | 2024-10-25 |  | PPC indicated that this could a VIBRO matter
| b | To minimize dust getting into the home I had to install air conditions in the home. Which now has a direct impact on the electricity bill and maintenance cost of these units. This reduced but did not solve the issue. | 2024-10-25 |  | PPC to advise
| c | Repairs to cracked boundary walls amongst other. | 2024-10-25 |  | PPC indicated that this could be a VIBRO matter
| d | In the attached pictures there are days that show how clear the air is when the mine is not in operation. | 2024-10-25 |  | Addressed in Item No.1 above
| e | In the sound clips which I have plenty more of, have nights when drilling is taking place around midnight and some on early hours of the morning and weekends. | 2024-10-25 |  | PPC indicated that this could be a VIBRO matter

## Reports Requested
ITEM No. | Report Requested | Date of Request | Submission Deadline | Report Submitted | Date of Submission
1 | A copy of the mine works programme | 2025/06/26 & 11 July 2025 | 2025-08-10
2 | A copy of the environmental management programme/plan | 2025/06/26 & 11 July 2025 | 2025-08-10
3 | A copy of the environmental impact assessment report | 2025/06/26 & 11 July 2025 | 2025-08-10
4 | All scientific reports that the mining company may have that show what the impacts of mining currently is | 2025/06/26 & 11 July 2025 | 2025-08-10
5 | Feedback reports from test conducted | 2025/06/26 & 11 July 2025 | 2025-08-10

## RSO_email 03102024
Dear Sir,
This email is aimed at formally advising PPC of the following and are not limited to:
Air pollution (see attached pictures)
I am writing to express my deep concern regarding the air pollution, noise pollution associated with the operations of the PPC Laudium Quarry. As a resident of Christoburg, I have noticed a significant increase in dust and particulate matter in the air, which I believe is directly linked to the mining activities in our vicinity.
The impact of this pollution on the health and well-being of our community is alarming. Many residents, including myself, have experienced respiratory issues, increased allergies, and other health complications that can be traced back to poor air quality. Additionally, the environmental consequences of such pollution are concerning; it affects local wildlife and vegetation, further degrading our natural surroundings. Not to mention the increase cost of maintenance of the property and vehicles. I’m unable to install Solar panels due to the regular maintenance it would require for optimum use.
I urge you to take immediate steps to mitigate the air pollution caused by your operations. Implementing stricter dust control measures, investing in cleaner technology, and ensuring compliance with environmental regulations are crucial steps that must be prioritized.
Transparency is essential in this matter. I request that you provide detailed information on the measures you are taking to address air quality concerns and the monitoring systems in place to ensure compliance with environmental standards.
Noise Pollution (refer to attached recordings)
The persistent noise from the mine at very odd hours has significantly affected the quality of life for us at home.
The continuous sounds of machinery, sirens, etc at odd hours of the night including weekends have not only disrupted our daily lives but have also led to increased stress, sleep deprivation and health issues. My family and I are finding it difficult to enjoy our home, especially during the evenings and weekends when we seek rest and relaxation.
I urge you to take immediate action to mitigate the noise pollution caused by your operations. Implementing effective noise reduction strategies, such as sound barriers and limiting operational hours, could significantly improve the situation.
Furthermore, I would appreciate any information you can provide regarding your current noise monitoring practices and any plans you have to address this ongoing issue. Transparency and communication with us are vital to building a positive relationship moving forward.
Vibrations (refer to attached recordings)
With regards to the vibrations caused by mining machinery and their impact on the structural integrity of my property. I have noticed significant disturbances resulting from your operations, which have begun to cause damage to my home.
The vibrations from the heavy machinery and blasting activities are not only disruptive but have also led to visible cracks in the walls and ceilings of my property. This situation is distressing and has raised concerns about the long-term safety and stability of my home.
I urge you to take immediate action to assess and address the impact of these vibrations. Implementing mitigation strategies—such as adjusting operational procedures or enhancing vibration monitoring—could help prevent further damage.
I would also appreciate any information you can provide regarding your current practices for monitoring vibrations and how you plan to address this issue moving forward. Open communication is crucial for fostering a positive relationship and ensuring that we feel safe in our home.
I have reason to believe that other residents in the community may be having the same issues.
Actions taken by me:
I had to replace all carpets with waterproof vinyl flooring as the carpets were getting damp due to cracks in the foundation believed to be caused by the vibrations caused by the mine. This was done post waterproofing works.
To minimize dust getting into the home I had to install air conditions in the home. Which now has a direct impact on the electricity bill and maintenance cost of these units. This reduced but did not solve the issue.
Repairs to cracked boundary walls amongst other.
In the attached pictures there are days that show how clear the air is when the mine is not in operation.
In the sound clips which I have plenty more of, have nights when drilling is taking place around midnight and some on early hours of the morning and weekends.
I appreciate your attention to this urgent issue and look forward to your prompt response.
8MB file was attached to this email submitted which contained evidances

## RSO_email 01112024
From: rashid@southafricantollagency.co.za <rashid@southafricantollagency.co.za>
Sent: Friday, 01 November 2024 11:13
To: 'Shadrack.molawa@ppc.co.za' <Shadrack.molawa@ppc.co.za>; 'Mary.Molaodi@ppc.co.za' <Mary.Molaodi@ppc.co.za>
Subject: PPC Pollution_462 Senorita str
Dear All,
Please find attached the concerns raised via email populated into a spreadsheet for tracking purposes.
It would be highly appreciated if the mine could provide feedback to columns “D” to “G” for now.
Let’s keep this as a live document providing feedback Biweekly.
Thanks and Kind Regards

## RSO_email 25032025
From: rashid@southafricantollagency.co.za <rashid@southafricantollagency.co.za>
Sent: Tuesday, 25 March 2025 01:22
To: 'Shadrack.molawa@ppc.co.za' <Shadrack.molawa@ppc.co.za>; 'Mary.Molaodi@ppc.co.za' <Mary.Molaodi@ppc.co.za>
Cc: 'enquiries@dmr.gov.za' <enquiries@dmr.gov.za>; 'contactus@ppc.co.za' <contactus@ppc.co.za>
Subject: Noice and Vibration_ongoing_RE: PPC Pollution_462 Senorita str
Importance: High
Dear Shadrack, Mary,
Since the day Shadrack and I had a chat a week ago with regards to points 2 and 3 of the attachment:
1. Noise Pollution
2. Vibration
I would like to reiterate that I am writing to formally express my serious concern regarding the excessive vibration and noise caused by your crusher. The intensity and frequency of these disturbances at odd hours of the night have resulted in severe sleep deprivation and are causing damage to my property.
Despite any prior attempts to tolerate the situation, the current level of disruption is entirely unacceptable. The continuous vibrations are affecting the structural integrity of my home, and the noise pollution is making it impossible to get adequate rest which at time is throughout the night. This issue must be addressed immediately before further harm is done. Attached are audio recordings for your records.
I expect the Mine to take urgent corrective action to mitigate these disturbances without delay. Since our meeting in October of 2024 the Mine’s senior management sent me on a wild goose chase directing my attention and this issue to VIBRO bricks. Investigation has proven it’s not them. If this issue is not resolved promptly, I will have no choice but to escalate the matter to the relevant authorities, including environmental and legal bodies. A wise person once said “ You can fool some of the people some of the time, but you can’t fool all of the people all of the time”.
Please confirm, in writing, the immediate steps you will take to rectify this situation. I expect a response within 48 hours to avoid further escalation. As my visit last week to the mine, discussing my concern with the Supervisor on site to stop this immediately after his call to Mary went on deaf ears.
I am extremely disappointed that the Mine has taken advantage of my patience and goodwill regarding the ongoing vibration and noise issues caused by your crusher. Despite my tolerance and reasonable expectations, the situation has not improved, and I feel completely disregarded.
I have shown understanding and restraint, yet my concerns about sleep deprivation and property damage have been ignored. This is unacceptable. I expected your company to act responsibly and address this issue without me having to continuously push for action.
I am now demanding an immediate and effective resolution.
NB: I’m addressing this issue now and in by no way or form must this be understood that there other issues have been resolved.
Kind Regards

## RSO_email 26062025
From: rashid@southafricantollagency.co.za <rashid@southafricantollagency.co.za>
Sent: Thursday, 26 June 2025 15:03
To: 'Shadrack.molawa@ppc.co.za' <Shadrack.molawa@ppc.co.za>; 'Mary.Molaodi@ppc.co.za' <Mary.Molaodi@ppc.co.za>
Cc: 'enquiries@dmr.gov.za' <enquiries@dmr.gov.za>; 'contactus@ppc.co.za' <contactus@ppc.co.za>; 'Vuyelwa.Siyeka@dmre.gov.za' <Vuyelwa.Siyeka@dmre.gov.za>
Subject: RE: Noice and Vibration_ongoing_RE: PPC Pollution_462 Senorita str
Dear Shadrack, Mary, CEO - Mr Matias Cardarelli,
W.R.T the trailing email, Whatsapp comms including recordings and telecoms which has resulted in very little being done to address my major concerns.
I write this email with deep frustration and immense disappointment. Despite previous attempts to raise my concerns with your company regarding the ongoing disturbances caused by your operations, it is abundantly clear that they have not been taken seriously, nor have any meaningful steps been taken to resolve them. The fact that your company states that the mine has been running for over 60 years and runs 24/7 does not give your company the right to ignore my concerns, more so when sleep deprivation is causing negative performance in the workplace for my wife and I.
Your mining operations have led to excessive air pollution, unrelenting noise levels, and strong ground vibrations that are not only violating my right to a peaceful environment but are also causing visible structural damage to my property. Cracks in the walls and foundations are now evident and growing as previously communicated. This is no longer a matter of inconvenience — it is damage to private property, and I hold your company accountable.
In addition, the persistent noise and vibration disturbances have made it nearly impossible to get proper rest, leading to severe sleep deprivation and a steady decline in my mental and physical well-being. My home — a place that should be a sanctuary — is fast becoming uninhabitable due to your negligence.
It is wholly unacceptable that your activities continue to compromise the health, safety, and basic human dignity of residents living near your site. I have been more than patient, hoping for a responsible and respectful response from your side. That patience has now run its course.
I am demanding the following immediate actions:
1. A full and independent assessment of the structural damage caused to my property — at your expense.
2. A formal plan of mitigation regarding air and noise pollution and ground vibrations.
3. A written response to this email within seven (7) calendar days outlining the measures you will take to address these matters. As your company has so far failed to reduce anything in writing.
Coupled with the above submission I request:
a. A copy of the mine works programme
b. A copy of the environmental management programme/plan and the environmental impact assessment report
c. All scientific reports that the mining company may have that show what the impacts of mining currently is
Failure to respond satisfactorily and without delay will leave me with no choice but to escalate this matter to the appropriate environmental and regulatory authorities, pursue legal action for damages, and seek relief through public and media channels if necessary.
This letter serves as a formal record of your awareness of the ongoing harm your operations are causing. Any further inaction on your part will be viewed as wilful negligence.
I trust you will treat this matter with the seriousness it warrants.
NB: still hoping for an amicable solution

## RSO_email 07072025
Dear Shadrack, Mary, Mr Matias Cardarelli,
Kindly be advised this is there last day to provide a response to the trailing email.
Kind Regards